## សង្ខេប
បែបបទត្រួតពិនិត្យ និងវាយតម្លៃការចូលរួមរបស់សមាជិកក្រុម
ប្រព័ន្ធគ្រប់គ្រងលិខិតអញ្ចើញឌីជីថល (E-Invitation) — បែបបទសវនកម្មការចូលរួម ការបំពេញភារកិច្ច និងការវាយតម្លៃសមិទ្ធផលក្រុម
គ្រប់ដំណើរការ ការងារ ការត្រួតពិនិត្យ QA/QC និងឯកសារ ត្រូវបញ្ចប់មិនលើសពីថ្ងៃទី ០១ ខែធ្នូ ឆ្នាំ ២០២៦
ព័ត៌មានគម្រោង |  |  | ចំនួនសមាជិក |  | ពិន្ទុមធ្យមក្រុម |  | ការងារសរុប |  | អត្រាបញ្ចប់
ថ្ងៃចាប់ផ្តើមត្រួតពិនិត្យ | 2026-09-09 |  | 6 |  |  |  | 37 |  | 51.35%
ថ្ងៃបញ្ចប់ចុងក្រោយ | 2026-12-01
រយៈពេលតាមដាន | ១២ សប្ដាហ៍
វដ្តត្រួតពិនិត្យ | ប្រចាំសប្ដាហ៍
សមាសធាតុវាយតម្លៃ និងទម្ងន់ពិន្ទុ | [5 empty] | ផែនការតាមដានរហូតដល់ថ្ងៃទី ០១ ធ្នូ ២០២៦
ល.រ | សមាសធាតុវាយតម្លៃ | ទម្ងន់ | ប្រភពភស្តុតាង | កំណត់សម្គាល់ |  | វគ្គ | រយៈពេល | គោលដៅ | Output / Evidence
1 | វត្តមាន | 10% | Weekly Audit | គណនាស្វ័យប្រវត្តិ |  | ១ | 09–15 Sep | ផ្ទៀងផ្ទាត់ Team Owner / GitHub / Evidence | Owner mapping + Audit baseline
2 | ការចូលរួម និងទំនាក់ទំនង | 10% | Meeting / Team | 0–100 |  | ២ | 16–30 Sep | Security remediation: credential + Git history | Incident closure evidence
3 | ការបំពេញការងារដែលបានចាត់តាំង | 25% | Task Tracker | 0–100 |  | ៣ | 01–27 Oct | Live integrations: Auth / ABA / Telegram / Email / Storage | Integration test evidence
4 | ការគោរព Deadline | 10% | Task Tracker | 0–100 |  | ៤ | 28 Oct–10 Nov | Deployment + Staging E2E / QA/QC | Deployment logs + E2E report
5 | គុណភាពការងារ | 15% | QA / Review | 0–100 |  | ៥ | 11–24 Nov | Documentation + A11y + Performance + Final Fix | Final report + optimization evidence
6 | Git / GitHub Contribution | 10% | PR / Commit / Issue | 0–100 |  | ៦ | 25 Nov–01 Dec | Final Regression / Code Freeze / Demo / Submission | Final build + archive + submission
7 | Testing / QA / Bug Fix | 5% | Test Evidence | 0–100
8 | Documentation / Report | 5% | Report / Document | 0–100 |  | កម្រិតវាយតម្លៃ
9 | Initiative & Problem Solving | 5% | Team Review | 0–100 |  | 90–100 | ល្អប្រសើរ | 80–89 | ល្អ
10 | Teamwork / Peer Support | 5% | Peer Review | 0–100 |  | 70–79 | មធ្យមល្អ | 60–69 | មធ្យម
[6 empty] | < 60 | ត្រូវកែលម្អ
កូដវត្តមាន៖ 1 = មានវត្តមាន ¦ L = យឺត ¦ P = មានច្បាប់ ¦ A = អវត្តមាន
ព័ត៌មានសវនកម្ម GitHub និងសមាជិកក្រុម
Repository | Ny-Panha/Koupreng-invitation_project |  |  | Branch | main | GitHub reviewed | 08-Sep-2026 | Deadline | 01-Dec-2026
Team Leader | កឿង វីរៈ (Koeurng Vireak) |  |  | Members | 6 | Mapped GitHub | 3 | Unmapped | 3
ល.រ | សមាជិកក្រុម |  | Name / GitHub |  | តួនាទី |  | ស្ថានភាពភស្តុតាង GitHub
1 | កឿង វីរៈ |  | Koeurng Vireak / KoeurngVireakk |  | ប្រធានក្រុម / Team Leader — Backend |  | ផ្ទៀងផ្ទាត់ — PR និង Commit ច្រើន
2 | ឡាំ គីមឡុង |  | Lam Kimlong / Kimlong1610 |  | Backend |  | ផ្ទៀងផ្ទាត់ — Backend/API documentation commits
3 | នី បញ្ញា |  | Ny Panha / Ny-Panha |  | Frontend — User & Admin |  | ផ្ទៀងផ្ទាត់ — Template/Seating/Dev workflow commits
4 | គក់ ស្រីផ្កាយ |  | Kouk SreyPkay |  | Frontend — User |  | មិនទាន់ផ្ទៀងផ្ទាត់ GitHub account
5 | រ៉ាន់ ណារ៉ាត់ |  | Ran Narath |  | Frontend — User |  | មិនទាន់ផ្ទៀងផ្ទាត់ GitHub account
6 | គុយ ដាលី |  | Kuy Daly |  | Backend |  | មិនទាន់ផ្ទៀងផ្ទាត់ GitHub account
គោលការណ៍សវនកម្ម៖ GitHub Commit/PR គឺជាភស្តុតាងបច្ចេកទេសដែលអាចតាមដានបាន ប៉ុន្តែមិនត្រូវប្រើជំនួសការវាយតម្លៃគុណភាព ការចូលរួមប្រជុំ Documentation Demo និងការងារមិនមែនកូដឡើយ។ សម្រាប់សមាជិកដែលមិនទាន់ផ្ទៀងផ្ទាត់ GitHub account ត្រូវប្រើ Task Tracker / Meeting Log / Report / Demo ជាភស្តុតាងបន្ថែម។

## វាយតម្លៃក្រុម
បែបបទត្រួតពិនិត្យ និងវាយតម្លៃការចូលរួមរបស់សមាជិកក្រុម
ប្រព័ន្ធគ្រប់គ្រងលិខិតអញ្ចើញឌីជីថល (E-Invitation) — ការវាយតម្លៃការចូលរួម និងការបំពេញភារកិច្ចប្រចាំសប្ដាហ៍
រយៈពេលត្រួតពិនិត្យ៖ 09-09-2026 ដល់ 01-12-2026 ¦ កាលបរិច្ឆេទបញ្ចប់ចុងក្រោយ៖ 01-12-2026
ល.រ | គោត្តនាម និងនាម | Name in English | តួនាទី / Role | វត្តមាន និងការចូលរួមតាមសប្ដាហ៍ | [11 empty] | សរុបវត្តមាន |  | ពិន្ទុវាយតម្លៃដើម (0–100) | [9 empty] | ពិន្ទុបម្លែងតាមទម្ងន់ | [9 empty] | លទ្ធផលសរុប
|  |  |  | 09–15 កញ្ញា | 16–22 កញ្ញា | 23–29 កញ្ញា | 30 កញ្ញា–06 តុលា | 07–13 តុលា | 14–20 តុលា | 21–27 តុលា | 28 តុលា–03 វិច្ឆិកា | 04–10 វិច្ឆិកា | 11–17 វិច្ឆិកា | 18–24 វិច្ឆិកា | 25 វិច្ឆិកា–01 ធ្នូ | ចំនួន 1 | % ចូលរួម | វត្តមាន | ចូលរួម/ ទំនាក់ទំនង | បំពេញ Assignment | គោរព Deadline | គុណភាព ការងារ | Git / GitHub | QA / Testing | ឯកសារ / Report | Initiative / Problem | Teamwork / Peer | វត្តមាន | ចូលរួម/ ទំនាក់ទំនង | បំពេញ Assignment | គោរព Deadline | គុណភាព ការងារ | Git / GitHub | QA / Testing | ឯកសារ / Report | Initiative / Problem | Teamwork / Peer | សរុប /100 | កម្រិត | ចំណាត់ថ្នាក់ | កំណត់សម្គាល់
|  |  |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 |  |  | 10% | 10% | 25% | 10% | 15% | 10% | 5% | 5% | 5% | 5% | 10% | 10% | 25% | 10% | 15% | 10% | 5% | 5% | 5% | 5%
1 | កឿង វីរៈ | Koeurng Vireak | ប្រធានក្រុម / Team Leader — Backend | [37 empty] | GitHub mapping ផ្ទៀងផ្ទាត់៖ KoeurngVireakk ¦ Team Leader ¦ ពិន្ទុសកម្មភាពមិនបំពេញស្វ័យប្រវត្តិ
2 | ឡាំ គីមឡុង | Lam Kimlong | Backend | [37 empty] | GitHub mapping ផ្ទៀងផ្ទាត់៖ Kimlong1610 ¦ ពិន្ទុត្រូវវាយតម្លៃជាមួយ Task/QA/Meeting evidence
3 | នី បញ្ញា | Ny Panha | Frontend — User & Admin | [37 empty] | GitHub mapping ផ្ទៀងផ្ទាត់៖ Ny-Panha ¦ ពិន្ទុត្រូវវាយតម្លៃជាមួយ Task/QA/Meeting evidence
4 | គក់ ស្រីផ្កាយ | Kouk SreyPkay | Frontend — User | [37 empty] | មិនទាន់ផ្ទៀងផ្ទាត់ GitHub account — ប្រើ Task, Meeting, Document និង Demo evidence
5 | រ៉ាន់ ណារ៉ាត់ | Ran Narath | Frontend — User | [37 empty] | មិនទាន់ផ្ទៀងផ្ទាត់ GitHub account — ប្រើ Task, Meeting, Document និង Demo evidence
6 | គុយ ដាលី | Kuy Daly | Backend | [37 empty] | មិនទាន់ផ្ទៀងផ្ទាត់ GitHub account — ប្រើ Task, Meeting, Document និង Demo evidence
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## តាមដានការងារ
បែបបទតាមដានការងារ និង Assignment របស់ក្រុម
តារាងតាមដានការងារ / ភារកិច្ច — ប្រព័ន្ធគ្រប់គ្រងលិខិតអញ្ចើញឌីជីថល (E-Invitation) ¦ ថ្ងៃផុតកំណត់ចុងក្រោយ៖ 01-Dec-2026
ចំណាំ៖ Deadline របស់ការងារទាំងអស់ត្រូវមិនលើសពីថ្ងៃទី ០១ ខែធ្នូ ឆ្នាំ ២០២៦។ Historical rows ប្រើ Completion Date ពី GitHub; Planned rows ប្រើ Target Deadline។
ល.រ | Task ID | ការងារ / Assignment | Module / Process | អ្នកទទួលខុសត្រូវ | Owner (English) | ថ្ងៃចាត់តាំង | Deadline | ថ្ងៃបញ្ចប់ | អាទិភាព | ស្ថានភាព | Progress % | Evidence / Link | Reviewer / QA | Quality /100 | Days Late | កំណត់សម្គាល់
1 | H-001 | Media management + template payment flow | Media / Payment | កឿង វីរៈ | Koeurng Vireak |  |  | 2026-05-26 | — | បានបញ្ចប់ | 100 | https://github.com/Ny-Panha/Koupreng-invitation_project/pull/2 |  |  |  | GitHub PR #2; media/storage/payment/Telegram implementation
2 | H-002 | Dynamic + Static ABA payment conflict resolution | Payment / Telegram | កឿង វីរៈ | Koeurng Vireak |  |  | 2026-06-03 | — | បានបញ្ចប់ | 100 | https://github.com/Ny-Panha/Koupreng-invitation_project/pull/3 |  |  |  | GitHub PR #3; backend tests 84
3 | H-003 | Account, payment, budget stabilization & Flyway safety | Backend / Database / Payment | កឿង វីរៈ | Koeurng Vireak |  |  | 2026-06-09 | — | បានបញ្ចប់ | 100 | https://github.com/Ny-Panha/Koupreng-invitation_project/pull/4 |  |  |  | GitHub PR #4; backend tests 124
4 | H-004 | Post-merge QA/security tooling | QA / Security | កឿង វីរៈ | Koeurng Vireak |  |  | 2026-06-09 | — | បានបញ្ចប់ | 100 | https://github.com/Ny-Panha/Koupreng-invitation_project/pull/7 |  |  |  | Security / CSV / audit IP hardening
5 | H-005 | Garden Royal Khmer template audit cleanup | Template / QA | កឿង វីរៈ | Koeurng Vireak |  |  | 2026-06-10 | — | បានបញ្ចប់ | 100 | https://github.com/Ny-Panha/Koupreng-invitation_project/pull/9 |  |  |  | Backend 127 tests; public parity and QA checklist
6 | H-006 | Khmer wedding template renderer iteration | Frontend / Template | កឿង វីរៈ | Koeurng Vireak |  |  | 2026-07-08 | — | បានបញ្ចប់ | 100 | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/2ba8578ff0b045f237e8277d326c4d969e2e647f |  |  |  | Dynamic/Premium/Garden Royal template work
7 | H-007 | Repository cleanup and repository-wide quality gates | QA / CI / Security | កឿង វីរៈ | Koeurng Vireak |  |  | 2026-07-21 | — | បានបញ្ចប់ | 100 | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/8ac78ee8d3fc3a74102441a0b0b69ee1d3d438ff |  |  |  | Cleanup, CI, security, Playwright route-smoke evidence
8 | H-008 | User/Admin feature modernization | Frontend / Admin | កឿង វីរៈ | Koeurng Vireak |  |  | 2026-08-07 | — | បានបញ្ចប់ | 100 | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/a56d0b49e74724c34faa90981d8eb4991cd0cf4a |  |  |  | Dashboard, builder, guest, budget, gifts, seating, admin
9 | H-009 | AI invitation writing assistant + helper triggers | AI / Frontend | កឿង វីរៈ | Koeurng Vireak |  |  | 2026-08-07 | — | បានបញ្ចប់ | 100 | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/c923eff5810d7d11f8312f6e409f0d39a88e041d |  |  |  | Invitation writing assistant
10 | H-010 | A–K full project flow QA verification | QA / E2E | កឿង វីរៈ | Koeurng Vireak |  |  | 2026-08-07 | — | បានបញ្ចប់ | 100 | https://github.com/Ny-Panha/Koupreng-invitation_project/pull/10 |  |  |  | 127 backend tests; lint/build; 22/22 route smoke
11 | H-011 | Dependency and business-flow hardening | Security / CI | កឿង វីរៈ | Koeurng Vireak |  |  | 2026-08-10 | — | បានបញ្ចប់ | 100 | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/57892c718869b4fc4bd80c47eb2b14c87c894547 |  |  |  | Backend dependency patch + CI sync
12 | H-012 | Legacy authentication storage fix | Authentication | ឡាំ គីមឡុង | Lam Kimlong |  |  | 2026-08-26 | — | បានបញ្ចប់ | 100 | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/481ab54194ef580f9b9be872c9b2da873315187c |  |  |  | Traceable commit by Kimlong1610
13 | H-013 | Dashboard/template catalog UI polish | Frontend / UI | នី បញ្ញា | Ny Panha |  |  | 2026-08-31 | — | បានបញ្ចប់ | 100 | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/d61d7b1a590093f5c673a7ee214be56132f60837 |  |  |  | Traceable commit by Ny-Panha
14 | H-014 | Feature modularization + wedding builder/test suites | Architecture / Frontend / Tests | នី បញ្ញា | Ny Panha |  |  | 2026-09-03 | — | បានបញ្ចប់ | 100 | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/36332bd59b5a2558a0fca69ff61ee9acdd2d8770 |  |  |  | Traceable commit by Ny-Panha
15 | H-015 | Canva-style seating floor plan | Seating / UI | នី បញ្ញា | Ny Panha |  |  | 2026-09-06 | — | បានបញ្ចប់ | 100 | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/d484ad24d2c1a9605f900e32670ba374492aecfb |  |  |  | Auto-arrange, anti-overlap, 100-table support
16 | H-016 | Secure OpenAPI + Scalar portal + dev fixtures | Backend / API Docs | ឡាំ គីមឡុង | Lam Kimlong |  |  | 2026-09-07 | — | បានបញ្ចប់ | 100 | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/4d6f27b68e68d4773a7c6faa0e98f4013115c651 |  |  |  | OpenAPI/Scalar development documentation
17 | H-017 | Swagger UI and API documentation settings | Backend / API Docs | ឡាំ គីមឡុង | Lam Kimlong |  |  | 2026-09-08 | — | បានបញ្ចប់ | 100 | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/468024ee6a17e161417f2154f2f9c1f9fb56d31a |  |  |  | Traceable commit by Kimlong1610
18 | H-018 | Team Git automation to prevent code collisions | Team Workflow / Git | នី បញ្ញា | Ny Panha |  |  | 2026-09-08 | — | បានបញ្ចប់ | 100 | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/c7512d6fdeae920bb4c1da031f852dd8ae7b517f |  |  |  | Team workflow evidence
19 | H-019 | Template live preview sync and curtain gate fix | Template / Frontend | នី បញ្ញា | Ny Panha |  |  | 2026-09-08 | — | បានបញ្ចប់ | 100 | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/59eec270c00e1d96d8b97b428a0fefcc6b77dde5 |  |  |  | Latest reviewed main commit
20 | P-001 | ផ្ទៀងផ្ទាត់ GitHub account និង Evidence របស់សមាជិកទាំង ៦ | Team Audit | ក្រុមទាំងមូល | Whole Team | 2026-09-09 | 2026-09-15 |  | ខ្ពស់ | កំពុងធ្វើ | 20 | វាយតម្លៃក្រុម + ភស្តុតាង GitHub | កឿង វីរៈ |  | 0 | ត្រូវ mapping សមាជិក 3 នាក់ទៀតដោយមិនសន្និដ្ឋាន
21 | P-002 | Rotate leaked/old Telegram credential និងកំណត់ incident owner | Security | ក្រុមទាំងមូល | Whole Team | 2026-09-09 | 2026-09-22 |  | បន្ទាន់ | គ្រោង | 0 | docs/security/credential-incident-response.md | ត្រូវចាត់តាំង |  | 0 | Release blocker from QA evidence
22 | P-003 | Git history remediation / Gitleaks 29 findings triage | Security / Git | ក្រុមទាំងមូល | Whole Team | 2026-09-16 | 2026-09-30 |  | បន្ទាន់ | គ្រោង | 0 | docs/qa/known-limitations.md | ត្រូវចាត់តាំង |  | 0 | Coordinate history rewrite and collaborator re-clone
23 | P-004 | Complete Java/Maven vulnerability advisory scan | Backend / Security | ក្រុមទាំងមូល | Whole Team | 2026-09-23 | 2026-10-06 |  | ខ្ពស់ | គ្រោង | 0 | docs/qa/known-limitations.md | ត្រូវចាត់តាំង |  | 0 | Current local OWASP report incomplete
24 | P-005 | Live Google + Telegram authentication validation | Authentication / Integration | ក្រុមទាំងមូល | Whole Team | 2026-10-01 | 2026-10-13 |  | ខ្ពស់ | គ្រោង | 0 | Integration evidence / screenshots | ត្រូវចាត់តាំង |  | 0 | External/manual validation required
25 | P-006 | Live ABA checkout/callback + Telegram payment detection test | Payment / Integration | ក្រុមទាំងមូល | Whole Team | 2026-10-07 | 2026-10-20 |  | បន្ទាន់ | គ្រោង | 0 | Payment test evidence | ត្រូវចាត់តាំង |  | 0 | Must verify real payment reconciliation
26 | P-007 | SMTP/email + storage/Cloudinary + DNS/TLS/CORS validation | Infrastructure / Integration | ក្រុមទាំងមូល | Whole Team | 2026-10-14 | 2026-10-27 |  | ខ្ពស់ | គ្រោង | 0 | Deployment configuration evidence | ត្រូវចាត់តាំង |  | 0 | External services validation
27 | P-008 | Staging deployment + Railway/service topology evidence | Deployment | ក្រុមទាំងមូល | Whole Team | 2026-10-21 | 2026-11-03 |  | ខ្ពស់ | គ្រោង | 0 | Deployment URL / logs / service mapping | ត្រូវចាត់តាំង |  | 0 | No Railway-ready claim until evidence exists
28 | P-009 | Full staging E2E: create/edit/publish/RSVP/admin/payment | QA / E2E | ក្រុមទាំងមូល | Whole Team | 2026-11-01 | 2026-11-10 |  | បន្ទាន់ | គ្រោង | 0 | Staging E2E report | ក្រុម QA |  | 0 | Representative staging data required
29 | P-010 | Accessibility + performance + large bundle optimization review | QA / UX / Performance | ក្រុមទាំងមូល | Whole Team | 2026-11-05 | 2026-11-17 |  | មធ្យម | គ្រោង | 0 | Lighthouse / a11y checklist / build metrics | ក្រុម QA |  | 0 | Includes focus, contrast, reduced motion, performance budgets
30 | P-011 | Final project report, API/ERD/architecture/user guide evidence | Documentation | ក្រុមទាំងមូល | Whole Team | 2026-11-11 | 2026-11-24 |  | ខ្ពស់ | គ្រោង | 0 | Final report / diagrams / appendix | កឿង វីរៈ |  | 0 | Align with university project paper guideline
31 | P-012 | Final demo, defense rehearsal, backup & recovery drill | Finalization | ក្រុមទាំងមូល | Whole Team | 2026-11-18 | 2026-11-27 |  | ខ្ពស់ | គ្រោង | 0 | Demo checklist / backup evidence | កឿង វីរៈ |  | 0 | All members participate
32 | P-013 | Final QA/QC, code freeze, evidence archive and submission | Project Closure | ក្រុមទាំងមូល | Whole Team | 2026-11-25 | 2026-12-01 |  | បន្ទាន់ | គ្រោង | 0 | Final build + submission package | កឿង វីរៈ |  | 0 | គ្រប់ Process ត្រូវបញ្ចប់ត្រឹម 01-Dec-2026
33 | W1-001 | Backend security/API regression + OWASP Java dependency report | Backend / Security / API | ឡាំ គីមឡុង | Lam Kimlong | 2026-09-10 | 2026-09-13 |  | ខ្ពស់ | គ្រោង | 0 | PR + mvn test output + OWASP dependency report | កឿង វីរៈ |  | 0 | Run backend tests; generate OWASP Java dependency report; verify Swagger/Scalar security/config; fix safe High/Critical findings. Branch: feat/week1-backend-security-api. Checkpoint: 12-Sep 18:00.
34 | W1-002 | Payment/Telegram backend integration readiness and regression tests | Backend / Payment / Telegram | គុយ ដាលី | Kuy Daly | 2026-09-10 | 2026-09-13 |  | ខ្ពស់ | គ្រោង | 0 | PR + Postman/mock evidence + backend test output | កឿង វីរៈ |  | 0 | Validate order/payment state flow, amount/order checks, duplicate confirmation/idempotency and Telegram/manual confirmation path using mock/local evidence when live provider access is unavailable. Branch: feat/week1-payment-integration-tests. Checkpoint: 12-Sep 18:00.
35 | W1-003 | User + Admin frontend integration regression and priority bug fixes | Frontend / User / Admin | នី បញ្ញា | Ny Panha | 2026-09-10 | 2026-09-13 |  | ខ្ពស់ | គ្រោង | 0 | PR + screenshots + lint/build/test evidence | កឿង វីរៈ |  | 0 | Test auth guards, dashboard, template create/edit/preview and admin user/template management; fix reproducible P0/P1 UI/API/route issues; ensure user/admin builds pass. Branch: fix/week1-user-admin-regression. Checkpoint: 12-Sep 18:00.
36 | W1-004 | User frontend responsive + accessibility QA and fixes | Frontend / User / UX / A11y | គក់ ស្រីផ្កាយ | Kouk SreyPkay | 2026-09-10 | 2026-09-13 |  | ខ្ពស់ | គ្រោង | 0 | PR + mobile screenshots + QA checklist | កឿង វីរៈ |  | 0 | Audit Dashboard, Template Catalog and Invitation Builder at 360/390/412px plus desktop; check overflow, forms, loading/error/empty states, keyboard/focus; fix high-impact issues. Branch: fix/week1-user-responsive-a11y. Checkpoint: 12-Sep 18:00.
37 | W1-005 | Public invitation + RSVP visual/functional QA | Frontend / Public / RSVP / Template QA | រ៉ាន់ ណារ៉ាត់ | Ran Narath | 2026-09-10 | 2026-09-13 |  | ខ្ពស់ | គ្រោង | 0 | PR or QA report + screenshots + defect checklist | កឿង វីរៈ |  | 0 | Review CanvaKhmerWeddingTemplate on mobile/desktop: typography/spacing, opening animation, RSVP, gallery, music, location and upload fallbacks; fix P0/P1 defects or document evidence if no code change. Branch: test/week1-public-rsvp-visual-qa. Checkpoint: 12-Sep 18:00.
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
Formulas:
Days Late = IF([Deadline]="","",IF([ថ្ងៃបញ្ចប់]<>"",MAX(0,[ថ្ងៃបញ្ចប់]-[Deadline]),IF(TODAY()>[Deadline],TODAY()-[Deadline],0)))

## កំណត់ប្រជុំ
កំណត់ហេតុប្រជុំ ការចូលរួម និងសកម្មភាពរបស់ក្រុម
កំណត់ត្រាកិច្ចប្រជុំ និងការចូលរួម — ប្រព័ន្ធគ្រប់គ្រងលិខិតអញ្ចើញឌីជីថល (E-Invitation) ¦ 09-Sep-2026 ដល់ 01-Dec-2026
ប្រើសន្លឹកនេះសម្រាប់កត់ត្រាប្រជុំពិតប្រាកដ៖ អ្នកចូលរួម សេចក្តីសម្រេច Action Items អ្នកទទួលខុសត្រូវ Due Date និង Evidence។ មិនបានបង្កើត Attendance ក្លែងក្លាយជាមុនទេ។
ល.រ | កាលបរិច្ឆេទ | សប្ដាហ៍ | ប្រធានបទប្រជុំ | អ្នកចូលរួម | អវត្តមាន/ច្បាប់ | សេចក្តីសម្រេចសំខាន់ | Action Items | អ្នកទទួលខុសត្រូវ | Due Date | ស្ថានភាព | Evidence / Link | កំណត់សម្គាល់
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## ប្រវត្តិគម្រោង
ប្រវត្តិការអភិវឌ្ឍគម្រោង និងសកម្មភាពសំខាន់ៗ
ប្រព័ន្ធគ្រប់គ្រងលិខិតអញ្ចើញឌីជីថល (E-Invitation) — Consolidated Project History ¦ បញ្ចប់គ្រប់ដំណើរការត្រឹម 01-Dec-2026
ល.រ | កាលបរិច្ឆេទ | ប្រភេទ | ដំណាក់កាល / ការងារ | សេចក្ដីសង្ខេប | អ្នកពាក់ព័ន្ធ | ស្ថានភាព | ភស្តុតាង / Reference
1 | 2026-03-14 | Project Analysis | System analysis, core features, DFD/ERD និង Security | វិភាគគំរូ E-Invitation, កំណត់ Core Features, សិក្សា DFD/ERD, WAF និង Payment flow សម្រាប់ប្រព័ន្ធ។ | ក្រុមគម្រោង / Team Leader | បានរៀបចំ | Project chat history
2 | 2026-05-06 | Project Setup | រៀបចំ Technology Stack និង Project Structure | Spring Boot + Maven, ReactJS/Vite, MySQL, FastAPI, Git និងការរៀបចំ backend/frontend structure។ | ក្រុមគម្រោង | បានរៀបចំ | Project chat history
3 | 2026-05-12 | Configuration | .env និង Google OAuth | រៀបចំ environment variables និង OAuth client configuration សម្រាប់ authentication។ | ក្រុមគម្រោង | បានរៀបចំ | Project chat history
4 | 2026-05-15 | Payment Design | ABA PayWay + Telegram confirmation | រចនា static ABA PayWay link, QR/deeplink និង semi-automatic Telegram payment confirmation ដោយមាន Order/User/Template evidence។ | Team Leader | បានរៀបចំ | Project chat history
5 | 2026-05-20 | Database | ERD និង Relational Design | រៀបចំ users, templates, invitations, sections, media, guests, RSVP, payments និង relationship សម្រាប់ MySQL/Flyway។ | ក្រុមគម្រោង | បានរៀបចំ | Project chat history
6 | 2026-05-26 | AI / Feature Planning | AI integration និង Payment/Media implementation planning | ពិភាក្សាការរួមបញ្ចូល AI/ML និងរៀបចំ implementation plan សម្រាប់ media និង template payment flow។ | Team Leader | បានរៀបចំ | Project chat history
7 | 2026-05-26 | GitHub PR | Media + Template Payment Flow | បន្ថែម media management, storage abstraction, media API/Flyway, static ABA payment, admin confirmation, frontend checkout និង Telegram bot។ | កឿង វីរៈ | បានបញ្ចប់ | https://github.com/Ny-Panha/Koupreng-invitation_project/pull/2
8 | 2026-06-03 | GitHub PR | Resolve Payment Conflict Flows | រក្សា dynamic ABA QR និងបន្ថែម static ABA/Telegram flow ជាមួយ backend security/testing។ | កឿង វីរៈ | បានបញ្ចប់ | https://github.com/Ny-Panha/Koupreng-invitation_project/pull/3
9 | 2026-06-06 | Integration | Frontend ↔ Backend + Flyway cleanup | រៀបចំការតភ្ជាប់ ReactJS និង Spring Boot និងសម្អាត database/entity/Flyway structure ដើម្បីរក្សា UI/UX របស់ក្រុម។ | ក្រុមគម្រោង | បានរៀបចំ | Project chat history
10 | 2026-06-09 | GitHub PR | Account/Payment/Budget Hardening | Stabilization, forward-only Flyway migration, static ABA safety, internal payment secret, auth/account/budget validation និង merge conflict cleanup។ | កឿង វីរៈ | បានបញ្ចប់ | https://github.com/Ny-Panha/Koupreng-invitation_project/pull/4
11 | 2026-06-09 | QA / Security | Post-merge QA + Security Hardening | QA audit tooling, admin login route, CSV/audit IP hardening និង browser smoke support។ | កឿង វីរៈ | បានបញ្ចប់ | https://github.com/Ny-Panha/Koupreng-invitation_project/pull/7
12 | 2026-06-10 | Template QA | Garden Royal Khmer Wedding Template | សម្អាត duplicate migration, កែ public parity, story sync និង update QA checklist សម្រាប់ Garden Royal template។ | កឿង វីរៈ | បានបញ្ចប់ | https://github.com/Ny-Panha/Koupreng-invitation_project/pull/9
13 | 2026-06-17 | AI / LLM | LLM Integration Review | ពិភាក្សាអំពីការរួមបញ្ចូល LLM សម្រាប់ invitation writing/smart suggestions និងការប្រើ AI ជាផ្នែកបន្ថែម។ | Team Leader / ក្រុមគម្រោង | បានរៀបចំ | Project chat history
14 | 2026-06-24 | QA | Smoke Test និង Production Readiness | កំណត់និយមន័យ Smoke Test និងការប្រើប្រាស់ក្នុង project QA/QC។ | ក្រុមគម្រោង | បានរៀបចំ | Project chat history
15 | 2026-06-24 | Architecture | Low-budget Deployment Architecture | Cloudflare → VPS/Nginx → Docker Compose services: React, Spring Boot, FastAPI, MySQL, Redis និង Telegram/payment worker។ | Team Leader / ក្រុមគម្រោង | បានរៀបចំ | Project chat history
16 | 2026-07-03 | Implementation | Khmer Wedding Template Iteration | Dynamic/Premium Canva Khmer wedding renderer, Garden Royal styling, location fallback និង visual improvements។ | កឿង វីរៈ | បានបញ្ចប់ | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/c6aa34ed8f72eeda3a35715e1e5053222ddac36c
17 | 2026-07-21 | Repository Audit | Repository Cleanup + QA/QC | សម្អាត unused assets/routes, រៀបចំ scripts, CI quality gates, backend migration gates, Playwright route smoke, security redaction និង QA evidence។ | កឿង វីរៈ | បានបញ្ចប់ | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/8ac78ee8d3fc3a74102441a0b0b69ee1d3d438ff
18 | 2026-08-07 | Feature Modernization | User/Admin Platform Modernization | Dashboard, invitation builder, AI writing assistant, organization workspace, guest management, budget, gifts, RSVP/check-in/seating និង admin workflows។ | កឿង វីរៈ | បានបញ្ចប់ | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/a56d0b49e74724c34faa90981d8eb4991cd0cf4a
19 | 2026-08-07 | QA | Verify A–K Project Flows | បន្ថែម full A–K QA report, route aliases, lint cleanup និង 22/22 route smoke verification។ | កឿង វីរៈ | បានបញ្ចប់ | https://github.com/Ny-Panha/Koupreng-invitation_project/pull/10
20 | 2026-08-10 | Security / CI | Business Flow + Dependency Hardening | Harden frontend/backend business flows, sync frontend dependencies/CI gates និង patch backend dependency vulnerabilities។ | កឿង វីរៈ | បានបញ្ចប់ | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/57892c718869b4fc4bd80c47eb2b14c87c894547
21 | 2026-08-26 | Authentication | Legacy session/auth storage improvement | កែ storage handling សម្រាប់ legacy session authentication និង initial state reading។ | ឡាំ គីមឡុង | បានបញ្ចប់ | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/481ab54194ef580f9b9be872c9b2da873315187c
22 | 2026-08-31 | UI / Dashboard | Dashboard & Template Catalog Polish | កែ draft 404 console errors និង polish template catalog/dashboard UI។ | នី បញ្ញា | បានបញ្ចប់ | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/d61d7b1a590093f5c673a7ee214be56132f60837
23 | 2026-08-31 | Documentation | Workflow Diagram | រៀបចំ workflow diagram សម្រាប់ project ដើម្បីបង្ហាញ process និង system flow។ | Team Leader | បានរៀបចំ | Project chat history
24 | 2026-09-03 | Architecture / Code | Feature Modularization | Modularize features, update wedding builder/templates និង backend test suites។ | នី បញ្ញា | បានបញ្ចប់ | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/36332bd59b5a2558a0fca69ff61ee9acdd2d8770
25 | 2026-09-06 | Seating | Canva-style Seating Floor Plan | Auto-arrange grid, anti-overlap និង support ដល់ 100 tables។ | នី បញ្ញា | បានបញ្ចប់ | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/d484ad24d2c1a9605f900e32670ba374492aecfb
26 | 2026-09-07 | Backend Docs | Secure OpenAPI / Scalar | Secure OpenAPI documentation, static analysis cleanup, Scalar API portal និង dev fixtures។ | ឡាំ គីមឡុង | បានបញ្ចប់ | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/4d6f27b68e68d4773a7c6faa0e98f4013115c651
27 | 2026-09-08 | Backend Docs | Swagger UI + API documentation settings | Enable Swagger UI និង update API documentation configuration។ | ឡាំ គីមឡុង | បានបញ្ចប់ | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/468024ee6a17e161417f2154f2f9c1f9fb56d31a
28 | 2026-09-08 | Team Workflow | Git automation to prevent code collisions | បន្ថែម team Git automation scripts សម្រាប់កាត់បន្ថយ merge/code collision។ | នី បញ្ញា | បានបញ្ចប់ | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/c7512d6fdeae920bb4c1da031f852dd8ae7b517f
29 | 2026-09-08 | Template Fix | Live Preview Sync / Curtain Gate | កែ live preview sync និង curtain gate style overlay ក្នុង dedicated layouts។ | នី បញ្ញា | បានបញ្ចប់ | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/59eec270c00e1d96d8b97b428a0fefcc6b77dde5
30 | 2026-09-09 | Audit | Team Participation & Contribution Report | រៀបចំ Excel audit form មាន weekly attendance, assignment, GitHub evidence, QA/QC, task tracker និង final deadline 01-Dec-2026។ | Team Leader / ក្រុមគម្រោង | កំពុងប្រើប្រាស់ | Project chat history

## ភស្តុតាង GitHub
ភស្តុតាងសកម្មភាព GitHub របស់ក្រុម
Repository: Ny-Panha/Koupreng-invitation_project ¦ Evidence reviewed through 08-Sep-2026 ¦ Commit/PR គឺជាភស្តុតាងបច្ចេកទេស មិនមែនជាពិន្ទុស្វ័យប្រវត្តិ
ល.រ | កាលបរិច្ឆេទ | សមាជិក | GitHub User | ប្រភេទ | PR / Commit | សេចក្ដីសង្ខេប | ស្ថានភាព | QA / Evidence Note | Link
1 | 2026-05-26 | កឿង វីរៈ | KoeurngVireakk | PR | #2 | Add media and template payment flows | Merged | Backend 72 tests; frontend build; Telegram compile | https://github.com/Ny-Panha/Koupreng-invitation_project/pull/2
2 | 2026-06-01 | កឿង វីរៈ | KoeurngVireakk | PR | #3 | Resolve payment conflict flows | Merged | Backend 84 tests; user/admin builds; Telegram compile | https://github.com/Ny-Panha/Koupreng-invitation_project/pull/3
3 | 2026-06-08 | កឿង វីរៈ | KoeurngVireakk | PR | #4 | Harden account, payment and budget recovery | Merged | Backend 124 tests; build/smoke validation | https://github.com/Ny-Panha/Koupreng-invitation_project/pull/4
4 | 2026-06-08 | កឿង វីរៈ | KoeurngVireakk | PR | #5 | Fix backend diagnostics | Closed / Not merged | 111 backend tests; frontend build | https://github.com/Ny-Panha/Koupreng-invitation_project/pull/5
5 | 2026-06-09 | កឿង វីរៈ | KoeurngVireakk | PR | #6 | Post-merge full project QA audit | Closed / Not merged | Backend 124 tests; 22 routes smoke | https://github.com/Ny-Panha/Koupreng-invitation_project/pull/6
6 | 2026-06-09 | កឿង វីរៈ | KoeurngVireakk | PR | #7 | Security / CSV export / audit IP hardening | Merged | Security hardening evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/pull/7
7 | 2026-06-09 | កឿង វីរៈ | KoeurngVireakk | PR | #8 | Restore post-merge QA tooling and admin login route | Merged | QA tooling restored | https://github.com/Ny-Panha/Koupreng-invitation_project/pull/8
8 | 2026-06-10 | កឿង វីរៈ | KoeurngVireakk | PR | #9 | Complete Garden Royal Khmer wedding template audit cleanup | Merged | Backend 127 tests; user/admin build; route smoke | https://github.com/Ny-Panha/Koupreng-invitation_project/pull/9
9 | 2026-06-16 | កឿង វីរៈ | KoeurngVireakk | PR | #10 | Verify A-K project flows | Merged | Backend 127 tests/package; lint/build; 22/22 route smoke | https://github.com/Ny-Panha/Koupreng-invitation_project/pull/10
10 | 2026-08-10 | កឿង វីរៈ | KoeurngVireakk | Commit | 57892c7 | Patch backend dependency vulnerabilities | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/57892c7
11 | 2026-08-10 | កឿង វីរៈ | KoeurngVireakk | Commit | 307dc4e | Synchronize frontend dependencies and CI gates | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/307dc4e
12 | 2026-08-10 | កឿង វីរៈ | KoeurngVireakk | Commit | 7811967 | Harden frontend and backend business flows | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/7811967
13 | 2026-08-10 | កឿង វីរៈ | KoeurngVireakk | Commit | 83bfaed | Implement mobile navigation sidebar and toggle functionality | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/83bfaed
14 | 2026-08-07 | កឿង វីរៈ | KoeurngVireakk | Commit | a56d0b4 | Complete platform management workflows | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/a56d0b4
15 | 2026-08-07 | កឿង វីរៈ | KoeurngVireakk | Commit | e5914d4 | Modernize RSVP check-in and seating | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/e5914d4
16 | 2026-08-07 | កឿង វីរៈ | KoeurngVireakk | Commit | f24a68c | Modernize wedding gift tracking | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/f24a68c
17 | 2026-08-07 | កឿង វីរៈ | KoeurngVireakk | Commit | 203a29a | Modernize budget and expense experience | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/203a29a
18 | 2026-08-07 | កឿង វីរៈ | KoeurngVireakk | Commit | 4581275 | Add dashboard insights and quick actions | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/4581275
19 | 2026-08-07 | កឿង វីរៈ | KoeurngVireakk | Commit | f78f671 | Modernize invitation builder workflow with AI helper triggers | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/f78f671
20 | 2026-08-07 | កឿង វីរៈ | KoeurngVireakk | Commit | c923eff | Add invitation writing assistant | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/c923eff
21 | 2026-08-07 | កឿង វីរៈ | KoeurngVireakk | Commit | 2e57454 | Add organization team workspace management | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/2e57454
22 | 2026-08-07 | កឿង វីរៈ | KoeurngVireakk | Commit | aa661b0 | Make backend authoritative for domain state; cleanup local fallbacks | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/aa661b0
23 | 2026-08-07 | កឿង វីរៈ | KoeurngVireakk | Commit | b5968e5 | Modularize guest management into clean domain architecture | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/b5968e5
24 | 2026-08-07 | កឿង វីរៈ | KoeurngVireakk | Commit | 2e7fefe | Standardize shared UI system primitives | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/2e7fefe
25 | 2026-08-07 | កឿង វីរៈ | KoeurngVireakk | Commit | 3b71c39 | Canonicalize host routes under /dashboard/* with legacy redirects | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/3b71c39
26 | 2026-08-07 | កឿង វីរៈ | KoeurngVireakk | Commit | 97e0a60 | Update current gap status and frontend/backend capability matrix | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/97e0a60
27 | 2026-08-07 | កឿង វីរៈ | KoeurngVireakk | Commit | b026f7a | Add comprehensive backend/frontend audit reports and test configs | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/b026f7a
28 | 2026-08-07 | កឿង វីរៈ | KoeurngVireakk | Commit | 3b045b3 | Add organization frontend API client | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/3b045b3
29 | 2026-08-07 | កឿង វីរៈ | KoeurngVireakk | Commit | 159e649 | Merge repository cleanup and QA into main | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/159e649
30 | 2026-08-07 | កឿង វីរៈ | KoeurngVireakk | Commit | 65c5e82 | Checkpoint local work before merge | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/65c5e82
31 | 2026-07-21 | កឿង វីរៈ | KoeurngVireakk | Commit | 405e8a2 | Separate backend static analysis gate | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/405e8a2
32 | 2026-07-21 | កឿង វីរៈ | KoeurngVireakk | Commit | 73c2266 | Restore complete deletion evidence | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/73c2266
33 | 2026-07-21 | កឿង វីរៈ | KoeurngVireakk | Commit | 71bb374 | Align asset report deliverable name | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/71bb374
34 | 2026-07-21 | កឿង វីរៈ | KoeurngVireakk | Commit | 89e060a | Avoid secret-shaped auth fixture | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/89e060a
35 | 2026-07-21 | កឿង វីរៈ | KoeurngVireakk | Commit | 438d345 | Record final browser evidence | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/438d345
36 | 2026-07-21 | កឿង វីរៈ | KoeurngVireakk | Commit | 4a9800e | Enforce route smoke with Playwright | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/4a9800e
37 | 2026-07-21 | កឿង វីរៈ | KoeurngVireakk | Commit | 5b7125b | Record cleanup evidence and release blockers | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/5b7125b
38 | 2026-07-21 | កឿង វីរៈ | KoeurngVireakk | Commit | c49828e | Refresh compatible frontend locks | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/c49828e
39 | 2026-07-21 | កឿង វីរៈ | KoeurngVireakk | Commit | 8ac78ee | Enforce repository-wide quality gates | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/8ac78ee
40 | 2026-07-21 | កឿង វីរៈ | KoeurngVireakk | Commit | df60f8b | Enforce backend quality and migration gates | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/df60f8b
41 | 2026-07-21 | កឿង វីរៈ | KoeurngVireakk | Commit | b604194 | Relocate and reconcile frontend source notes | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/b604194
42 | 2026-07-21 | កឿង វីរៈ | KoeurngVireakk | Commit | 6f0176b | Organize reusable automation scripts | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/6f0176b
43 | 2026-07-21 | កឿង វីរៈ | KoeurngVireakk | Commit | fd9a35e | Consolidate routes and remove legacy code | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/fd9a35e
44 | 2026-07-21 | កឿង វីរៈ | KoeurngVireakk | Commit | 400c92d | Remove generated files and unused media | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/400c92d
45 | 2026-07-21 | កឿង វីរៈ | KoeurngVireakk | Commit | 7e89241 | Remove exposed credentials and redact logs | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/7e89241
46 | 2026-07-08 | កឿង វីរៈ | KoeurngVireakk | Commit | 2ba8578 | Add cover Khmer golden wedding template | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/2ba8578
47 | 2026-07-07 | កឿង វីរៈ | KoeurngVireakk | Commit | 4c8d02b | Add Khmer golden invitation template | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/4c8d02b
48 | 2026-07-03 | កឿង វីរៈ | KoeurngVireakk | Commit | c6aa34e | Harden Canva Khmer wedding renderer | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/c6aa34e
49 | 2026-07-03 | កឿង វីរៈ | KoeurngVireakk | Commit | 7f7c05c | Add premium Canva Khmer wedding renderer | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/7f7c05c
50 | 2026-07-03 | កឿង វីរៈ | KoeurngVireakk | Commit | e28c3b6 | Build premium Canva Khmer invitation | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/e28c3b6
51 | 2026-07-03 | កឿង វីរៈ | KoeurngVireakk | Commit | 1b1e62d | Refine Canva Khmer wedding template | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/1b1e62d
52 | 2026-07-03 | កឿង វីរៈ | KoeurngVireakk | Commit | d2f6b01 | Add dynamic Canva Khmer wedding template | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/d2f6b01
53 | 2026-07-03 | កឿង វីរៈ | KoeurngVireakk | Commit | 970e190 | Enhance location section with loading state and fallback UI | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/970e190
54 | 2026-07-03 | កឿង វីរៈ | KoeurngVireakk | Commit | 3619740 | Add Garden Royal Sambot CSS styles for template experience | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/3619740
55 | 2026-09-08 | នី បញ្ញា | Ny-Panha | Commit | 59eec270 | Fix template live preview sync and curtain gate overlay | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/59eec270
56 | 2026-09-08 | នី បញ្ញា | Ny-Panha | Commit | c7512d6f | Add team Git automation scripts to prevent code collisions | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/c7512d6f
57 | 2026-09-06 | នី បញ្ញា | Ny-Panha | Commit | d484ad24 | Enhance seating floor plan with Canva-style canvas, auto-arrange, anti-overlap and 100-table support | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/d484ad24
58 | 2026-09-03 | នី បញ្ញា | Ny-Panha | Commit | 36332bd5 | Modularize features; update wedding builder/templates/backend test suites | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/36332bd5
59 | 2026-08-31 | នី បញ្ញា | Ny-Panha | Commit | d61d7b1a | Fix dashboard 404 draft errors; polish template catalog and dashboard UI | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/d61d7b1a
60 | 2026-08-31 | នី បញ្ញា | Ny-Panha | Commit | bafbcace | Update project features and improvements | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/bafbcace
61 | 2026-09-08 | ឡាំ គីមឡុង | Kimlong1610 | Commit | 4e451cf6 | Merge branch main of project repository | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/4e451cf6
62 | 2026-09-08 | ឡាំ គីមឡុង | Kimlong1610 | Commit | 468024ee | Enable Swagger UI and update API documentation settings | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/468024ee
63 | 2026-09-07 | ឡាំ គីមឡុង | Kimlong1610 | Commit | 4d6f27b6 | Add Scalar API portal and development fixtures | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/4d6f27b6
64 | 2026-09-07 | ឡាំ គីមឡុង | Kimlong1610 | Commit | 3dc60b38 | Resolve backend static analysis findings | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/3dc60b38
65 | 2026-09-07 | ឡាំ គីមឡុង | Kimlong1610 | Commit | 17575f41 | Add secure OpenAPI documentation | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/17575f41
66 | 2026-08-26 | ឡាំ គីមឡុង | Kimlong1610 | Commit | 481ab541 | Improve storage handling for legacy session auth and initial state reading | On main / traceable | Commit history evidence | https://github.com/Ny-Panha/Koupreng-invitation_project/commit/481ab541
សម្គាល់៖ មិនទាន់រកឃើញ GitHub identity ដែលអាចផ្ទៀងផ្ទាត់ដោយទំនុកចិត្តសម្រាប់ គក់ ស្រីផ្កាយ, រ៉ាន់ ណារ៉ាត់ និង គុយ ដាលី។ កុំសន្និដ្ឋានថាពួកគេមិនបានចូលរួម; ត្រូវប្រើ Assignment, Meeting, Documentation, Demo ឬ Evidence ផ្សេងៗសម្រាប់ Audit។

## QA-QC និងបញ្ហា
ស្ថានភាព QA/QC ភស្តុតាង និង Release Blockers
QA evidence date: 21-Jul-2026 ¦ Repository history reviewed through 08-Sep-2026 ¦ ត្រូវ rerun full verification មុន Final Submission 01-Dec-2026
ល.រ | ផ្នែក QA/QC | ការត្រួតពិនិត្យ / Command | លទ្ធផល Evidence 21-Jul-2026 | ស្ថានភាព | ចំណុចត្រូវធ្វើបន្ទាប់ | Target | Reference
1 | Backend Full Gate | mvnw clean verify | PASS: 128 tests, 0 failures/errors, 1 opt-in skip; JaCoCo; SpotBugs High 0; PMD 0 | PASS | Rerun against final code | 01-Dec-2026 | docs/qa/verification-results.md
2 | Backend Security Focus | Selected security/reset/logging tests | PASS: 6 tests | PASS | Rerun after security remediation | 01-Dec-2026 | docs/qa/verification-results.md
3 | Fresh MySQL + Flyway | FreshDatabaseMigrationTests | PASS: 15 migrations; ddl-auto=validate | PASS | Normalize migration naming only by approved forward strategy | Before final | docs/qa/verification-results.md
4 | User Frontend | lint + Vitest + Knip + depcheck + Vite build | PASS; 724 modules; JS bundle above Vite 500k warning | PASS / Warning | Review code-splitting/performance budget | 17-Nov-2026 | docs/qa/verification-results.md
5 | Admin Frontend | lint + Vitest + Knip + depcheck + Vite build | PASS | PASS | Rerun final build | 01-Dec-2026 | docs/qa/verification-results.md
6 | Browser E2E | Playwright desktop Chromium + Pixel 7 | PASS: 52 tests; 8 critical journeys + 44 route-smoke | PASS | Run full staging E2E against real services | 10-Nov-2026 | docs/qa/verification-results.md
7 | Route Smoke | 22 user/admin route shells desktop + mobile | PASS: 44 controlled cases | PASS | Repeat after final UI merge | 01-Dec-2026 | docs/qa/verification-results.md
8 | Telegram Service | pytest + Ruff + Bandit + compileall | PASS: 24 tests and static/compile gates | PASS | Add live Telegram integration validation | 13-Oct-2026 | docs/qa/verification-results.md
9 | Python Vulnerability Audit | pip-audit | PASS: no known vulnerabilities | PASS | Rerun before release | 01-Dec-2026 | docs/qa/verification-results.md
10 | Node Vulnerability Audit | npm audit --audit-level=high | PASS: 0 vulnerabilities | PASS | Rerun both frontend apps | 01-Dec-2026 | docs/qa/verification-results.md
11 | Secret Scan Current Tree | Gitleaks clean exported tree | PASS: 0 findings | PASS | Keep secret scan in final CI | 01-Dec-2026 | docs/qa/verification-results.md
12 | Secret Scan Git History | Gitleaks full-history diagnostic | FAIL/INCIDENT: 29 findings across 12 path/rule groups | BLOCKER | Rotate credentials + coordinated history rewrite | 30-Sep-2026 | docs/qa/known-limitations.md
13 | Java Advisory Feed | Maven dependency security profile | INCOMPLETE: no report before 10-minute timeout | BLOCKER | Obtain successful CI/provider vulnerability report | 06-Oct-2026 | docs/qa/known-limitations.md
14 | Railway / Deployment Evidence | Provider binding/topology/logs | Not verified / unavailable in audit evidence | BLOCKER | Provide service topology, variables, deployment logs and verified URL | 03-Nov-2026 | docs/qa/known-limitations.md
15 | Live External Integrations | Google, Telegram, ABA, SMTP, Cloudinary, DNS/TLS | Manual/live validation not yet evidenced | PENDING | Complete live/staging validations | 27-Oct-2026 | docs/qa/known-limitations.md
16 | Accessibility / Performance | Keyboard, screen reader, focus, contrast, reduced motion, performance | Not fully validated | PENDING | Complete a11y and performance review | 17-Nov-2026 | docs/qa/known-limitations.md
17 | Final Full Regression | All modules + final deployment | Not run yet against final code | PLANNED | Run final regression, archive evidence and freeze release | 01-Dec-2026 | Final audit plan
Release Blockers ដែលត្រូវបិទមុន 01-Dec-2026
ល.រ | Blocker | ស្ថានភាពបច្ចុប្បន្ន | សកម្មភាពត្រូវធ្វើ | Target | Owner
1 | Credential rotation | Old/exposed Telegram credential requires rotation | Rotate via BotFather, update deployment secrets, verify old token dead | 22-Sep-2026 | ក្រុមទាំងមូល
2 | Git history remediation | 29 Gitleaks findings / 12 groups | Triage + git filter-repo + coordinated force-push + re-clone | 30-Sep-2026 | ក្រុមទាំងមូល
3 | Java dependency advisory | Local advisory run incomplete | Get successful CI/provider dependency vulnerability report | 06-Oct-2026 | ក្រុមទាំងមូល
4 | Deployment evidence | Railway/service topology not verified | Provide status, services, vars (redacted), logs, domains, DB mapping | 03-Nov-2026 | ក្រុមទាំងមូល
5 | Asset rights | Retained music/gallery rights not documented | Record license/source or replace assets before production | 17-Nov-2026 | ក្រុមទាំងមូល

## ការងារសប្ដាហ៍នេះ
ផែនការចាត់តាំងការងារប្រចាំសប្ដាហ៍
ប្រព័ន្ធគ្រប់គ្រងលិខិតអញ្ចើញឌីជីថល (E-Invitation)
រយៈពេលការងារ៖ 10–13 September 2026 ¦ Checkpoint៖ Saturday 12-Sep-2026 18:00 ¦ Final Deadline៖ Sunday 13-Sep-2026 23:59
ល.រ | សមាជិក | តួនាទី | Assignment សំខាន់ | Deliverables / Evidence | Acceptance Criteria | Branch | Priority | Status | Deadline
1 | ឡាំ គីមឡុង Lam Kimlong | Backend | Backend security/API regression + OWASP Java dependency report | PR, mvn test output, OWASP report, Swagger/Scalar verification evidence | Backend tests PASS; dependency report generated; safe High/Critical findings fixed or documented; API docs remain correctly protected/configured | feat/week1-backend-security-api | ខ្ពស់ | គ្រោង | 2026-09-13
2 | គុយ ដាលី Kuy Daly | Backend | Payment/Telegram backend integration readiness + regression tests | PR, Postman/mock evidence, test output | Order/amount validation, payment-state transitions and duplicate-confirmation/idempotency tested; Telegram/manual confirmation path documented; backend tests PASS | feat/week1-payment-integration-tests | ខ្ពស់ | គ្រោង | 2026-09-13
3 | នី បញ្ញា Ny Panha | Frontend — User & Admin | User + Admin frontend integration regression + P0/P1 fixes | PR, screenshots, lint/build/test evidence | Auth guards, dashboard, template create/edit/preview and admin user/template management tested; no reproducible P0/P1 route/API mismatch remains; builds PASS | fix/week1-user-admin-regression | ខ្ពស់ | គ្រោង | 2026-09-13
4 | គក់ ស្រីផ្កាយ Kouk SreyPkay | Frontend — User | User frontend responsive + accessibility QA and fixes | PR, 360/390/412px screenshots, QA checklist | Dashboard, Template Catalog and Builder usable on target widths; no critical horizontal overflow; forms/loading/error/empty states and keyboard/focus reviewed; build PASS | fix/week1-user-responsive-a11y | ខ្ពស់ | គ្រោង | 2026-09-13
5 | រ៉ាន់ ណារ៉ាត់ Ran Narath | Frontend — User | Public invitation + RSVP visual/functional QA | PR or QA report, mobile/desktop screenshots, defect checklist | CanvaKhmerWeddingTemplate reviewed for typography/spacing/opening/RSVP/gallery/music/location/upload fallbacks; P0/P1 fixed or clearly evidenced; public flow works without broken assets | test/week1-public-rsvp-visual-qa | ខ្ពស់ | គ្រោង | 2026-09-13
របៀប Submit និង Definition of Done
1 | ប្រើ Branch ផ្ទាល់ខ្លួនតាមឈ្មោះដែលបានកំណត់ ហើយបង្កើត Pull Request; មិន Push ទៅ main ដោយផ្ទាល់។
2 | រាល់ Assignment ត្រូវមាន Evidence: PR/Commit link + Test output + Screenshot/Checklist ឬ Report តាមប្រភេទការងារ។
3 | Checkpoint ថ្ងៃសៅរ៍ 12-Sep-2026 ម៉ោង 18:00 — ត្រូវបង្ហាញ Progress, បញ្ហា/Blocker និង Evidence ដំបូង។
4 | Final Deadline ថ្ងៃអាទិត្យ 13-Sep-2026 ម៉ោង 23:59 — PR និង Evidence ត្រូវ Ready for Review; បញ្ហាដែលមិនអាចដោះស្រាយត្រូវមាន Root Cause + Next Action។
5 | ការងារត្រូវបានចាត់ទុកថា Complete លុះត្រាតែ Acceptance Criteria បានបំពេញ និង Team Leader Review Evidence រួច។